## Monthly Calendar
Trident Warrior '13 Calendar of Events aboard R/V Knorr
Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday
JUNE
KNORR MAINTENANCE PERIOD
SCANEAGLE PREMOBILIZATION1
SHORE CRANE
Chad Smith unavailable5
JULY
KNORR MAINTENANCE PERIOD
TRANSIT RIDER PREMOBILIZATION2
Chad Smith unavailable
KNORR MAINT.
TRANSIT RIDER PREMOBILIZATION2 |  |  |  | MOBILIZATION3
| TRANSIT 1: Woods Hole > Norfolk |  |  |  |  | ON MISSION
SHORE CRANE
DEMOBILIZATION4
ON MISSION: Trident Warrior '13 | [5 empty] | TRANSIT 2: Norfolk >
SHORE CRANE
TRANSIT 2: Norfolk > Woods Hole
1 Scaneagle Premobilization Objectives:
Crane SkyHook (3500lbs - has four designated lift points for crane) onto Knorr in the port aft corner of the main deck
Setup SkyHook and test out the desired location and clearances on flight deck
Crane aft antenna pedestal for Directional #2 (250lbs) on the 01 deck on the port side of the trash van
Bolt 30"x30" pedestal mounting plate to the 01 deck beside the trash van and attach antenna pedestal to the mounting plate
Setup AIS transmitter and simulate UAV GPS position transmissions to verify Knorr AIS display picks it up.
Bolt forward antenna pedestal for Directional #1 (no crane required) to the short ~3-4ft tall post already on Knorr in the forward starboard corner of the 02 deck
Attach forward Omni #1 antenna to the starboard side of the foremast on the forward 02 deck
Attach Omni #2 antenna to the port side of the forward railing on the 04 deck.
These operations will be the responsibility of the Science Party, take place with the discretion of the Master of the Knorr and with limited shore/crew support
2 Transit Rider Premobilization Objectives:
Loading of the Wave Gliders, Buoys, SLOCUM Gliders and associated hand carry equipment for planned transit deployments
Personnel under Co-Chief Sci Kipp Shermann from OSU. (14 total on Transit +1 WHOI Trustee)
These operations will be the responsibility of the Science Party, take place with the discretion of the Master of the Knorr and with limited shore/crew support
3 Mobilization:
All remaining equipment to be loaded including aircraft and both control vans.
This operation has the complete support of the Knorr crew.
4 Demobilization
Complete demobilization of all Trident Warrior equipment while docked in Norfolk.
5 Coordinator Unavailable:
Chad Smith (WHOI) Will be on international travel on these dates with limited phone and email.
Contact: Eric Benway (WHOI) at 508-289-3770 or ebenway@whoi.edu during these dates
23
24
25
26
27
28
29
30
1
2
3
4
5
6
7
8
9
10
11
12
13
20
19
18
17
16
15
14
21
22