## Sheet1
ADEON Preliminary Cruise Plan (as of 2017.07.26) for NOV/DEC 2017 RV ARMSTRONG
|  | Event | Cumulative | Cumulative
Event | Location | Duration (hrs) | Time (hrs) | Time (days) | Notes
Transit from WH to Virginia Intercanyon Stn (~ 330 n.mi) | Transit | 35 | 35 | 1.4583
AZFP calibration | VA | 6 | 41 | 1.7083 | Order of events at each station is flexible – want to make sure that net tows can be done at night
CTD cast (shallow site) | VA | 4 | 45 | 1.875 | factor of 2 in event duration to account for hiccups first time through
Net tow (shallow site) | VA | 4 | 49 | 2.0417 | factor of 2 in event duration to account for hiccups first time through
Deploy mooring (shallow site) | VA | 16 | 65 | 2.7083 | factor of 2 in event duration to account for hiccups first time through
Finescale Acoustic Survey Transect | VA | 14 | 79 | 3.2917 | factor of 2 in event duration to account for hiccups first time through
Transit – VA to Hat (130 n.mi.) | Transit | 15 | 94 | 3.9167
CTD cast (shallow site) | Hat | 2 | 96 | 4
Net tow (shallow site) | Hat | 2 | 98 | 4.0833
Deploy mooring (shallow site) | Hat | 8 | 106 | 4.4167
Finescale Acoustic Survey Transect | Hat | 8 | 114 | 4.75
Transit – Hat to Wilm (125 n.mi.) | Transit | 13 | 127 | 5.2917
CTD cast (shallow site) | Wilm | 2 | 129 | 5.375
Net tow (shallow site) | Wilm | 2 | 131 | 5.4583
Deploy mooring (shallow site) | Wilm | 8 | 139 | 5.7917
Finescale Acoustic Survey Transect | Wilm | 8 | 147 | 6.125
Transit – Wilm to Sav-Deep (105 n.mi) | Transit | 11 | 158 | 6.5833
CTD cast (deep site) | Sav-Deep | 4 | 162 | 6.75
Net tow (deep site) | Sav-Deep | 4 | 166 | 6.9167
Deploy mooring (deep site) | Sav-Deep | 12 | 178 | 7.4167
Finescale Acoustic Survey Transect | Sav-Deep | 8 | 186 | 7.75
Transit – Sav-Deep to Sav-Shal (55 n.mi.) | Transit | 6 | 192 | 8
CTD cast (shallow site) | CB | 2 | 194 | 8.0833
Net tow (shallow site) | CB | 2 | 196 | 8.1667
Deploy mooring (shallow site) | CB | 8 | 204 | 8.5
Finescale Acoustic Survey Transect | CB | 8 | 212 | 8.8333
TL Measurements – Site #1 | TL | 24 | 236 | 9.8333
Transit – Sav-Shal to 30N-Shall (130 n.mi.) | Transit | 13 | 249 | 10.375
CTD cast (shallow site) | 30N-Shallow | 2 | 251 | 10.4583
Net tow (shallow site) | 30N-Shallow | 2 | 253 | 10.5417
Deploy mooring (shallow site) | 30N-Shallow | 8 | 261 | 10.875
Finescale Acoustic Survey Transect | 30N-Shallow | 8 | 269 | 11.2083
TL Measurements – Site #2 | TL | 24 | 293 | 12.2083
Transit – 30N-Shallow to 29N-Deep (125 n.mi) | Transit | 13 | 306 | 12.75
CTD cast (deep site) | 29N-Deep | 4 | 310 | 12.9167
Net tow (deep site) | 29N-Deep | 4 | 314 | 13.0833
Deploy mooring (deep site) | 29N-Deep | 12 | 326 | 13.5833
Finescale Acoustic Survey Transect | 29N-Deep | 8 | 334 | 13.9167
Transit – 29N Deep to Wilmington (280 n.mi) | Transit | 28 | 362 | 15.0833
Transit – Wilimington to Hatteras (125 n.mi) | Transit | 13 | 375 | 15.625
Transit – Hatteras to Virginia (130 n.mi) | Transit | 13 | 388 | 16.1667
Recover mooring | VA-2 | 4 | 392 | 16.3333 | Possibly include 2nd round of CTD, net, finescale acoustic surveys.
Turnaround mooring | VA-2 | 4 | 396 | 16.5
Redeploy mooring | VA-2 | 4 | 400 | 16.6667
Transit – VA to Woods Hole (~ 330 n.mi) | Transit | 33 | 433 | 18.0417
Cruise Plan Activity Duration |  |  | 433 | 18.0417
Buffer to account for weather / sea-state (5 days) |  |  | 120 | 5
Total Cruise Time Planned |  |  | 553 | 23.0417
Total Transit Time |  | 193 | hrs
Total Time at station VA |  | 44
Total Time at station Hat |  | 20
Total Time at station Wilm |  | 20
Total Time at station Sav-Deep |  | 28
Total Time at station CB |  | 20
Total Time at station 30N-Shallow |  | 20
Total Time at station 29N-Deep |  | 28
Total Time at station VA-2 |  | 12
Total time on TL measurements |  | 48
Total time allotted for weather delays |  | 120
| checksum | 553