DART FIELD SERVICE PLAN Rev 1

TASK ORDER NUMBER: 183970.11.10039.01.04.002 (TO39 CY5 DART O&M-FS Labor)

183970.11.10039.01.04.102 (TO39 CY5 DART O&M-FS CPAY Labor)

FSP:			10087

STATIONS: 		44401 & 44402

CRUISE:		OC462

START DATE:  	20 May 2010

END DATE: 		31 May 2010

Appendix 1: DART Trip Report FSP 07132 of 17 Sep 07

Appendix 2: DART Trip Report FSP 09196 of 22 Jul 09

Appendix 3: DART Engineering Trip Report FSP 09196 of 20 Jul 09

Appendix 4: DART Acoustic Release Codes

Appendix 5: Pre-Sail Safety

Appendix 6: DART BPR Mooring Diagram (2)

Appendix 7: DART Buoy Mooring Diagram (2)

Appendix 8: Service Metadata Lists (2)

Appendix 9: Siting Diagrams (2)

Appendix 10: Site Status Logs (2)

Appendix 11: DART Refurbishment Integration and Test (RIT) Process

Appendix 12: P09-0012 DART II Pre-Deployment Dockside Test

Appendix 13: P08-0047 DART II Buoy and BPR Deployment

Appendix 14: ETP 09-003 DART II Buoy and BPR Recovery Procedures

Appendix 15: NTSC M-01-002 Service Visit to Buoys

Appendix 16: NTSC S.02.003 Return of Government Property for Field Service Activity

Appendix 17: NTSC H.29.001 Small Boat Instructions

Appendix 18: NTSC H.18.000 Accident/Injury Reporting

Approved by:       ______________________________

Kirk R. Benson

DART Project Manager

SUMMARY OF WORK

DART Team of Chris Obenhaus (DART Field Service Technician/Chief Scientist), and Lee Tretbar (DART Senior Mechanical Technician), with NDBC observer Bill Hansen, will depart Stennis Space Center and proceed to Woods Hole, MA to load and board the Research Vessel (R/V) OCEANUS in order to conduct service visits at DART Stations 44402 and 44401. Appendices 1-18 are provided as guidance.

Prior to getting underway, the DART Team members will meet with the crew of the R/V Oceanus to discuss the upcoming deployment. Cruise discussions will involve the details of the intended buoy operations, as described below, and safety issues.

| Station/Hull | Designated Location | Estimated Depth (Meters) | Notes |
| --- | --- | --- | --- |
| 44401 Station 44401 BPR | 37° 33’ 44” N 50° 00’ 00” W 37° 33’ 03” N 49° 59’ 08” W | 5374 5391 |  |
| 44402 Station 44402 BPR | 39° 29’ 14” N 70° 35’ 38” W 39° 29’ 13” N 70° 35’ 39” W | 2431 2434 |  |

NOTE: Before commencing buoy operations, it is important that each of the persons involved know their role on the deck of the ship.  The utilization of taglines to control the movement of all DART equipment is imperative, especially when transporting equipment over the water. Prior to buoy operations, all parties involved must meet to discuss a plan of deployment to ensure the safety of the team and equipment.

Contact Requirements

-----------------------------------

It is imperative that the Field Service Technician checks in on a daily basis, with the DART Data Analyst and DART Project Manager/DART Field Service Lead at SAIC, to ensure management is updated on the current status of the field service as well as to receive any updates to this document, or other directions, which may be pertinent. The following matrix defines when to contact NDBC.

| When to Contact | Who to Contact | Via |
| --- | --- | --- |
| Daily | Project Manager & Data Analyst | Satellite Phone |
| ETA to Station (Update as Required) | Project Manager/Data Analyst | ***Email |
| Arrival On Station (if different than ETA) | **Data Analyst | Satellite Phone |
| BPR Recovery (Provide position/time) | *Data Analyst | ***Email |
| Prior to BPR Deployment | Data Analyst | Satellite Phone |
| Following BPR Settling on Bottom | **Data Analyst | Satellite Phone |
| Prior to Release from Station | *Data Analyst | Satellite Phone |
| Any issues effecting service visit | Project Manager/Data Analyst | Satellite Phone |

* Data Analyst will notify the DART Project Manager via Email

** Data Analyst will notify the DART Project Manager via Telephone

*** If Available

NOTE: DART systems will be dock-side tested prior to being released for loading. Each system is required to pass a 12 hour dock-side test (See P09-0012: Pre-Deployment Dockside Test).  See Appendix 12.

NOTE: Buoy operations will be conducted in accordance with P08-0047: DART II Buoy and BPR Deployment and ETP 09-003: DART II Buoy and BPR Recovery Procedures. See Appendices 13 & 14.

NOTE: One DART Station on this leg are scheduled for hardware and firmware modifications to correct known problems and enhance functionality.  The Field Service Technician will be required to implement these changes in the field.  It is imperative the Field Service Technician take measures to ensure he is familiar with these changes.  Upgrades to hardware and firmware will not be completed on just the BPR or the buoy; they must be done on both the BPR and buoy payloads.

Service at 44401

-----------------------------------

Station 44401 Required Equipment

- DART II Buoy (Upgraded hardware/firmware/diodes installed)

-DART II BPR (Upgraded hardware/firmware/diodes installed)

-Anchor, BPR

This station was last serviced on 31 August 2007. Upon arriving at DART Station 44401, the team will begin buoy operations. Buoy operations will consist of recovering the existing BPR then recovering the buoy on deck.  The existing buoy mooring will be recovered utilizing a line cutter. A new buoy containing new batteries and payloads with upgraded hardware and firmware (version 2.39) will be deployed on a new mooring on station. A new BPR, with upgraded hardware and firmware will then be deployed.  Following confirmation that the BPR has reached the ocean floor, a three point acoustic triangulation method will be conducted, as feasible, to confirm the BPR position, utilizing the Angulate program.

NOTE: Prior to deploying and following recovery of any BPR, it is imperative to take appropriate Paros Oscillator Frequency checks and record them with the time taken (in GMT). Please ensure this data in entered into your trip report.

NOTE: Prior to deploying the new BPR, when formatting the flash card, give the filename of the station being deployed (44401.dat). This will aid in easier identification and tracking of the BPR data.

NOTE:  Prior to deploying the BPR, initiate a screen capture of all BPR data.  Submit this with your trip report.

Following the service visit of DART Station 44401, the ship will remain on station for verification of the next scheduled 6-hour data transmission to the RUDICS Server. This will be coordinated with the DAC, DART Analyst or DART Project Manager. Once the block of hourly transmitted data is verified by the National Data Buoy Center (NDBC), the ship will be released from station.

Note: The recovered LRUs from the station will be tagged and returned to NDBC, as appropriate. See Appendix 16.

Note:  The buoy mooring recovered from this station will be delivered to WHOI for analysis.

Service at 44402

-----------------------------------

Station 44402 Required Equipment

-DART II Buoy Payload and Batteries (Diodes Installed)

This station was last serviced on 16 July 2009. Upon arriving at DART Station 44402, the team will begin buoy operations. Buoy operations will consist of recovering the existing buoy on deck.  Once the buoy mooring is secured, the existing buoy payloads and batteries will be removed and replaced with new payloads and new batteries.

Following the service visit of DART Station 44402, the ship will remain on station for verification of the next scheduled 6-hour data transmission to the RUDICS Server. This will be coordinated with the DAC, DART Analyst or DART Project Manager. Once the block of hourly transmitted data is verified by the National Data Buoy Center (NDBC), the ship will be released from station.

Note: The recovered LRUs from the station will be tagged and returned to NDBC, as appropriate. See Appendix 16.

ESTIMATE OF DART FIELD SERVICE MAN HOURS

Personnel:	2

Days:  		17

Hours:

Field Service Regular:		64

Field Service Overtime:	48

CPAY Regular:		112

CPAY Weekend:		96

SAFETY

A Supervisors Accident/Incident Investigation Report form is attached in Appendix 18.  This form should be completed within 24 hours after the incident/accident. If an accident/incident occurs, obtain the report number from NTSC Operations.

POINTS OF CONTACT

SAIC

Data Assembly Center (DAC): (228) 688-2835

Tracy Boudreaux: Office: (228) 688-3716, Home: (601) 889-1385, Cell: (601) 590-0163

Kirk Benson: Office: (228) 688-1737, Home: (985) 643-2916, Cell: (228) 671-9621

John Tancredi: Office: (228) 688-2050

Stephanie Jordan: Office: (228) 688-3456, Cell: (228) 216-9187

IT Help Desk: During Work Hours: (228) 688-1415, After Hours: (228) 216-3731

SAIC International Security Manager, Jason Dury: (703) 676-5874 or (571) 337-0081

SAIC Asst to Dir of International Business, Laurie Pfeiffer:  (805) 682-0639 or (805) 284-5570

NDBC

Craig Kohler: Office: (228) 688-1421

Karen Grissom (DART Operations Mgr): Office: (228) 688-1325, Cell: (757) 469-6603

Dr. Chung-Chu Teng: Office: (228) 688-7101

SPECIAL EQUIPMENT

Laptop Computers (2) *

* - These items must be taken on cruise. DART personnel will maintain continuous accountability of government/SAIC computer equipment.

SHIP/VESSEL INFORMATION

Vessel:  R/V Oceanus

Embark Location: Woods Hole, MA

R/V Oceanus
Woods Hole Oceanographic Institution
266 Woods Hole Rd.
Woods Hole, MA  02543

POC: Mr. Eric Benway

(508) 289-3770

ebenway@whoi.edu

Debark Location: Woods Hole, MA

R/V Oceanus
Woods Hole Oceanographic Institution
266 Woods Hole Rd.
Woods Hole, MA  02543

POC: Mr. Eric Benway

(508) 289-3770

ebenway@whoi.edu

DART ACOUSTIC RELEASE CODES (Appendix 4)

Station 44402

Property #:  CD0001694597	Serial #:   31997

Release: 546307 			Int: 	 11 kHz

Enable:   556736			Rep: 	 12 kHz

Disable:   556753

Station 44401

Property #:  CD0000768991	Serial #:  31876

Release:	 543553			Int: 	 9 kHz

Enable:   536774			Rep: 	 10 kHz

Disable:   537001

PRE-SAIL SAFETY (Appendix 5)

PRE-LOAD TO DO:

· TALK TO THE CREW ABOUT PLACEMENT OF EQUIPMENT

- EQUIPMENT SHOULD BE LOADED IN ORDER OF SERVICES TO BE     DONE

- EQUIPMENT SHOULD BE LOADED AND SAFELY FASTENED TO THE DECK OF THE SHIP TO ENSURE CREW SAFETY AND EQUIPMENT SAFETY

PRE-DEPLOYMENT/SERVICE TO DO:

· TEAM SHOULD DISCUSS WITH CREW A PRE-DEPLOMENT/SERVICE GAME PLAN BEFORE EACH BUOY OPERATIONS

- DISCUSS WHO IS THE LEAD ON THE DECK DURING OPERATIONS

- HOW WILL THE BPR BE DEPLOYED/RETRIEVED

- ONCE BPR IS ON DECK, WHO WILL HAVE TAG LINES

- WHERE WILL THE TAG LINES BE ON THE BPR (CHECK ALL TAG LINE ANGLES FOR SAFETY)

NOTE:  SAFETY IS MOST IMPORTANT.  IF A TEAM MEMBER IS HURT, THE MISSION IS A FAILURE.

DECK LEAD_______________________________________

ALL PARTIES INVOLVED

__________________________________________________

__________________________________________________

__________________________________________________

__________________________________________________

__________________________________________________

__________________________________________________

| Service Metadata List |  |  |  |  |  |  |  |  |  |  | I:\DART Administrative\DART Deployment LRU Lists\FSP.xls |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Station: | 44401 |  |  |  |  | DATE: |  |  |  |  | Techs: |  |  |  |  |
| Hull: |  |  | Ship: |  |  |  | Time On Station |  |  |  | Time Released |  |  |  |  |
|  |  |  |  |  |  | Installed |  |  |  |  | Removed/Recovered |  |  |  |  |
| BUOY DATA |  | Deployed Date/time |  |  |  | PRIMARY |  |  | ID |  | PRIMARY |  |  |  |  |
| Lattitude D/M/S |  |  |  |  |  | Payload LRU #: * |  |  |  |  | Payload LRU #: |  |  |  |  |
| Longitude D/M/S |  |  |  |  |  | Iridium Antenna LRU #: |  |  |  |  | Iridium Antenna LRU #: |  |  |  |  |
| Water Depth (ship) |  |  |  |  |  | Iridium Modem LRU #: |  |  |  |  | Iridium Modem LRU #: |  |  |  |  |
| Depth Description |  |  |  |  |  | Transducer LRU #: |  |  |  |  | Transducer LRU #: |  |  |  |  |
| Mooring date | Old New |  |  |  |  | O&I Light LRU #: |  |  |  |  | O&I Light LRU #: |  |  |  |  |
| Stainless Steel |  | Galvanized |  |  |  | Data #: * |  |  |  |  | Data #: |  |  |  |  |
| Fishbite | Unitrex | Nilspin |  |  |  | SECONDARY |  |  | ID |  | SECONDARY |  |  |  |  |
| Paint job | Red/White Yellow |  |  |  |  | Payload LRU #:* |  |  |  |  | Payload LRU #: |  |  |  |  |
| BPR DATA |  |  |  |  |  | Iridium Antenna LRU #: |  |  |  |  | Iridium Antenna LRU #: |  |  |  |  |
| Deployed Date/time |  |  |  |  |  | Iridium Modem LRU #: |  |  |  |  | Iridium Modem LRU #: |  |  |  |  |
| Lattitude D/M/S |  |  |  |  |  | Transducer LRU #: |  |  |  |  | Transducer LRU #: |  |  |  |  |
| Longitude D/M/S |  |  |  |  |  | Data #: * |  |  |  |  | Data #: |  |  |  |  |
| DEPTH |  |  |  |  |  | BPR |  |  |  |  | BPR |  |  |  |  |
| Time on Bottom |  |  |  |  |  | CPU LRU #: * |  |  |  |  | CPU LRU #: |  |  |  |  |
| UPGRADE STATUS |  |  |  |  |  | PAROS LRU #: * |  |  |  |  | PAROS LRU #: |  |  |  |  |
| Firmware version |  | 2.0 | 2.1 |  |  | Serial number: |  |  |  |  | Serial number: |  |  |  |  |
| C34 Capacitor |  | No | Yes |  |  | Transducer LRU #:* |  |  |  |  | Transducer LRU #: |  |  |  |  |
| O-Rings |  | 70 | 90 |  |  | Acoustic Rls LRU# * |  |  | S/N |  | Acoustic Rls LRU# |  |  | S/N |  |
| Diodes installed |  | No | Yes |  |  | New Codes | E | D | R |  | Old Codes | E | D | R |  |
| BPR Cables |  | Seacon | Subcon |  |  | Pre Clock Chect |  |  |  |  | Post Clock check |  |  |  |  |
|  |  |  |  |  |  | Pre Oscill Freq |  |  |  |  | Post Oscill Freq |  |  |  |  |
| Comments: |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |

| Service Metadata List |  |  |  |  |  |  |  |  |  |  | I:\DART Administrative\DART Deployment LRU Lists\FSP.xls |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Station: | 44402 |  |  |  |  | DATE: |  |  |  |  | Techs: |  |  |  |  |
| Hull: |  |  | Ship: |  |  |  | Time On Station |  |  |  | Time Released |  |  |  |  |
|  |  |  |  |  |  | Installed |  |  |  |  | Removed/Recovered |  |  |  |  |
| BUOY DATA |  | Deployed Date/time |  |  |  | PRIMARY |  |  | ID |  | PRIMARY |  |  |  |  |
| Lattitude D/M/S |  |  |  |  |  | Payload LRU #: * |  |  |  |  | Payload LRU #: |  |  |  |  |
| Longitude D/M/S |  |  |  |  |  | Iridium Antenna LRU #: |  |  |  |  | Iridium Antenna LRU #: |  |  |  |  |
| Water Depth (ship) |  |  |  |  |  | Iridium Modem LRU #: |  |  |  |  | Iridium Modem LRU #: |  |  |  |  |
| Depth Description |  |  |  |  |  | Transducer LRU #: |  |  |  |  | Transducer LRU #: |  |  |  |  |
| Mooring date | Old New |  |  |  |  | O&I Light LRU #: |  |  |  |  | O&I Light LRU #: |  |  |  |  |
| Stainless Steel |  | Galvanized |  |  |  | Data #: * |  |  |  |  | Data #: |  |  |  |  |
| Fishbite | Unitrex | Nilspin |  |  |  | SECONDARY |  |  | ID |  | SECONDARY |  |  |  |  |
| Paint job | Red/White Yellow |  |  |  |  | Payload LRU #:* |  |  |  |  | Payload LRU #: |  |  |  |  |
| BPR DATA |  |  |  |  |  | Iridium Antenna LRU #: |  |  |  |  | Iridium Antenna LRU #: |  |  |  |  |
| Deployed Date/time |  |  |  |  |  | Iridium Modem LRU #: |  |  |  |  | Iridium Modem LRU #: |  |  |  |  |
| Lattitude D/M/S |  |  |  |  |  | Transducer LRU #: |  |  |  |  | Transducer LRU #: |  |  |  |  |
| Longitude D/M/S |  |  |  |  |  | Data #: * |  |  |  |  | Data #: |  |  |  |  |
| DEPTH |  |  |  |  |  | BPR |  |  |  |  | BPR |  |  |  |  |
| Time on Bottom |  |  |  |  |  | CPU LRU #: * |  |  |  |  | CPU LRU #: |  |  |  |  |
| UPGRADE STATUS |  |  |  |  |  | PAROS LRU #: * |  |  |  |  | PAROS LRU #: |  |  |  |  |
| Firmware version |  | 2.0 | 2.1 |  |  | Serial number: |  |  |  |  | Serial number: |  |  |  |  |
| C34 Capacitor |  | No | Yes |  |  | Transducer LRU #:* |  |  |  |  | Transducer LRU #: |  |  |  |  |
| O-Rings |  | 70 | 90 |  |  | Acoustic Rls LRU# * |  |  | S/N |  | Acoustic Rls LRU# |  |  | S/N |  |
| Diodes installed |  | No | Yes |  |  | New Codes | E | D | R |  | Old Codes | E | D | R |  |
| BPR Cables |  | Seacon | Subcon |  |  | Pre Clock Chect |  |  |  |  | Post Clock check |  |  |  |  |
|  |  |  |  |  |  | Pre Oscill Freq |  |  |  |  | Post Oscill Freq |  |  |  |  |
| Comments: |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |

DART BPR Mooring

Appendix 6

DART Buoy Mooring

Appendix 7

DART Refurbishment Integration and Test (RIT) Process (Appendix 11)

- Prepare hull prior to arrival at next station as follows (not necessarily in this order):

  - Remove payloads/batteries

  - Inspect hull/bridle/mast for damage

  - Ensure any sea life is scraped from hull

  - Paint hull (yellow on top, anti-fouling red on bottom)

  - Replace zinc anodes

  - Inspect bumper

  - Inspect radar reflector

  - Replace O&I light (if > 2 years)

  - Inspect/replace gaskets on lid/faceplate

  - Inspect/replace cable connectors on faceplate

  - Inspect/replace transducer cables/connectors

  - Inspect battery carriage

  - Install new batteries

  - Inspect/refill hydrogen getter

  - Install payloads

  - Hook up battery/transducer cables

  - Inspect/test payloads

  - Scrape/paint on bridle

  - Scrape/paint/replace Transducer Housing/Cover Weldments

  - Replace zinc anodes on bridle

- Prepare BPR prior to arrival at next station as follows (not necessarily in this order):

  - Remove flash card, label it, and store it in a secure location for return to the Lab

  - Remove any sea life

  - Inspect/replace O-rings on battery cans

  - Install/test acoustic release

  - Inspect/test BPR CPU/Paros for proper operation

  - Install BPR CPU/Paros on BPR

  - Replace batteries

  - Inspect/Install cables

  - Attach BPR to BPR Anchor Weldment

  - Clean/inspect/repair BPR mooring