## Sheet1
AT26-14
notes: | general plan is for Alvin dive at 8, CTD cast over site after recovery, transit to next site, launch Sentry, recover in time for Alvin lanuch
time for Sentry dive is estimated based on the general plan, may not launch if < 8 hrs
basic basket plan is for 8-10 large quivers and stoppers, 2 bioboxes, niskin rack with pump + wand, 6 push cores
modified with addition of Bushmaster, staining device (TBD) on some dives
weather contingencies are CTD casts at deeper sites and multibeam over some exploratory sites
date | Sentry | Alvin | lat | long | depth | transit to site | Sentry time | Alvin tasks (roughly prioritized)
2013-04-27 |  | Gulfport
2013-04-28 |  | VK826 | 29.1565 | -88.0164 | 487.45 | 120 | 3.675 | coral collections in quivers/biobox, niskins, lighting and camera set up, push cores
2013-04-29 | VK826 Sam's Hill survey | VK826 | 29.1565 | -88.0164 | 487.45 | 0 | 15.675 | more coral collections, niskins, push cores, exploration
2013-04-30 | VK906 pCO2/mosaic | VK906 | 29.0689 | -88.3776 | 400.31 | 23 | 13.4331 | collections, niskins, cores
2013-05-01 | exploratory in MC | MC885 | 28.0647 | -89.6951 | 627 | 93 | 6.282 | Corals near seeps, stain corals, niskins near Lophelia
2013-05-02 | AT357 pCO2/mosaic | AT357 | 27.5868 | -89.7045 | 1050 | 29 | 12.4 | Paramuricea near seeps, cores, madrepora collection niskins
2013-05-03 | exploratory in MC | MC751 | 28.1939 | -89.7986 | 440.84 | 38 | 11.9061 | callo near seeps, bushmaster tw, cores
2013-05-04 | GC234 pCO2/N transects | GC234 | 27.7469 | -91.2245 | 500 | 80 | 7.6667 | tubeworms survey, callo transect, Lophelia heading N, bushmaster near corals, cores
2013-05-05 | GC354 pCO2/transects | GC354 | 27.6005 | -91.8238 | 515 | 33 | 12.3567 | lophelia niskins, sponges, bushmaster tubeworms, cores
2013-05-06 | GB535 pCO2/NE transects | GB535 | 27.4302 | -93.5776 | 512.13 | 94 | 6.2586 | coral collecitons, niskins, explore NE
2013-05-07 | 2 best GB sites | GB |  |  | 512 | 40 | 11.6587 | explore, lophelia/callo pop gen, niskins, new monitoring (or more GB535 NE if interesting)
2013-05-08 | 2 more GB sites | GB |  |  | 512 | 40 | 11.6587 | explore, lophelia/callo pop gen, niskins, new monitoring
2013-05-09 | exploratory in GC | GC354 |  |  | 515 | 94 | 6.2567 | lophelia niskins, sponges, bushmaster coral near tw collection
2013-05-10 | seep to coral pCO2 | GC234N |  |  | 480 | 33 | 12.38 | Lophelia, callo/seep explore to N, bushmaster coral near tw
2013-05-11 | exploratory in GC | GC |  |  |  | 40 | 12 | new site?
2013-05-12 | AT357 pCO2/mosaic | AT357 |  |  | 627 | 90 | 6.582 | new part of site? Seep/coral cores
2013-05-13 | exploratory in MC | MC |  |  |  | 40 | 12 | or callo/seep part of 862?
2013-05-14 | seep to coral pCO2 | VK826 |  |  | 487 | 100 | 5.6753 | mop up, live corals, niskins
2013-05-15 | VK906 pCO2/mosaic | VK906 |  |  | 400 | 23 | 13.4333 | mop up, live corals, niskins
2013-05-16 |  | Gulfport |  |  |  | 120