## Dive Schedule
AT36 Dive Locations
Color indicates a Sentry map/Alvin dive pair
Date | Alvin | Sentry | Ship-Side Deployment (CTD, coring) | Notes
2016-07-28 | NO DIVE (transit) | Veatch Canyon 2 | Veatch Canyon 2 (area) | Sentry produced map of Veatch Canyon 2 to be used to plan Alvin dive there on Jul-30 (during Leg 1)
2016-07-29 | Engineering Dive TBD | New England Seep 2 | New England Seep 2 (area) | Sentry produced map of New England Seep 2 to be used to plan Alvin dive there on Jul-31 (during Leg 1)
2016-07-30 | Veatch Canyon 2 | Veatch Canyon 1 | Veatch Canyon 1 (area) | Sentry produced map of Veatch Canyon 1 to be used to plan Alvin dive there on Aug-06 (during leg 2)
2016-07-31 | New England Seep 2 | New England Seep 3 | New England Seep 3 (area) | Sentry produced map of New England Seep 3 to be used to plan Alvin dive there on Aug-05 (during leg 2)
2016-08-01 | Shallop Canyon West (Bounce Dive) | NO DIVE (transit) | Shallop Canyon West (area)
2016-08-02 | NO DIVE (transit) | [8/3 early AM] Shallop Canyon East | Shallop Canyon East (area) | Sentry produced map of Shallop Canyon East to be used to plan Alvin dive there on Aug-04 (during leg 2)
2016-08-03 | Hydrographer Coral 2 | Shallop Canyon West | Shallop Canyon West (area) | Alvin dive location selected by coral focused participants. Alvin dive of Aug-01 used to plan/inform Sentry mission. | Possible PIT
2016-08-04 | Shallop Canyon East (Bounce Dive) | New England Seep 2 | New England Seep 2 (area) | Alvin dive of Jul-31 used to plan/inform Sentry mission. (Sentry mission may be abbreviated due to preceding Alvin bounce dive)
2016-08-05 | New England Seep 3 | Veatch Canyon 2 | Veatch Canyon 2 (area) | Sentry dive location and modality TBD based on participant needs. Also may be used if a previous Sentry dive on the cruise is postponed | Possible PIT
2016-08-06 | Veatch Canyon 1 | NO DIVE (transit) | Veatch Canyon 1 (area)
Dive Site | LAT | LON | DEPTH (m)
Veatch Canyon 1 | 39.8112 | -69.5898 | 1405.1
Veatch Canyon 2 | 39.8061 | -69.5922 | 1423.8
New England Seep 3 | 39.8674 | -69.2841 | 1139.1
New England Seep 2 | 39.9019 | -69.2553 | 1476.1
Shallop Canyon West | 39.9966 | -69.1914 | 373.5
Shallop Canyon East | 39.9974 | -69.1209 | 299.5
Hydrographer Coral 2 | 40.0533 | -69.0355 | 908.3

## Hour by Hour
Alvin Dive
Sentry Dive
Atlantis Transit
Over the Side Operations: CTD / Multicore / Gravity Core
Over the Side Operations During Sentry Dive (At Discretion of Sentry Team)
Vehicles
| 0:00 | 0:30 | 1:00 | 1:30 | 2:00 | 2:30 | 3:00 | 3:30 | 4:00 | 4:30 | 5:00 | 5:30 | 6:00 | 6:30 | 7:00 | 7:30 | 8:00 | 8:30 | 9:00 | 9:30 | 10:00 | 10:30 | 11:00 | 11:30 | 12:00 | 12:30 | 13:00 | 13:30 | 14:00 | 14:30 | 15:00 | 15:30 | 16:00 | 16:30 | 17:00 | 17:30 | 18:00 | 18:30 | 19:00 | 19:30 | 20:00 | 20:30 | 21:00 | 21:30 | 22:00 | 22:30 | 23:00 | 23:30
2016-07-28 | [12 empty] | Atlantis Transit | [27 empty] | Sentry Veatch Canyon 2
2016-07-29 | CTD/Multicore | [15 empty] | Alvin Engineering | [22 empty] | Sentry New England Seep 2
2016-07-30 | CTD/Multicore | [15 empty] | Alvin Veatch Canyon 2 | [22 empty] | Sentry Veatch Canyon 1
2016-07-31 | CTD/Multicore | [15 empty] | Alvin New England Seep 2 | [22 empty] | Sentry New England Seep 3
2016-08-01 | CTD/Multicore | [15 empty] | Alvin Shallop Canyon West [Bounce 1] | [10 empty] | Alvin Shallop Canyon West [Bounce 2] | [8 empty] | CTD/Multicore
2016-08-02
2016-08-03 |  |  |  | Sentry Shallop Canyon East | [12 empty] | Alvin Hydrographer Coral 2 | [22 empty] | Sentry Shallop Canyon West | Sentry Shallop Canyon West
2016-08-04 | CTD/Multicore | [15 empty] | Alvin Shallop Canyon East [Bounce 1] | [10 empty] | Alvin Shallop Canyon East [Bounce 2] | [11 empty] | Sentry New England Seep 2 | Sentry New England Seep 2
2016-08-05 | CTD/Multicore | [15 empty] | Alvin Dive New England Seep 3 | [24 empty] | Sentry Veatch Canyon 2 | Sentry Veatch Canyon 2
2016-08-06 | CTD/Multicore | [15 empty] | Alvin Veatch Canyon 1
2016-08-07
Shipboard /Telepresence Events
| 0:00 | 0:30 | 1:00 | 1:30 | 2:00 | 2:30 | 3:00 | 3:30 | 4:00 | 4:30 | 5:00 | 5:30 | 6:00 | 6:30 | 7:00 | 7:30 | 8:00 | 8:30 | 9:00 | 9:30 | 10:00 | 10:30 | 11:00 | 11:30 | 12:00 | 12:30 | 13:00 | 13:30 | 14:00 | 14:30 | 15:00 | 15:30 | 16:00 | 16:30 | 17:00 | 17:30 | 18:00 | 18:30 | 19:00 | 19:30 | 20:00 | 20:30 | 21:00 | 21:30 | 22:00 | 22:30 | 23:00 | 23:30
2016-07-28 | [23 empty] | Lunch |  |  | Planning | [8 empty] | Dinner | Sci Debrief |  |  |  | Reports
2016-07-29 | [14 empty] | Breakfast | [5 empty] | Training
2016-07-30
2016-07-31 | [32 empty] | AMNH Rehr.
2016-08-01
2016-08-02
2016-08-03 | [32 empty] | AMNH
2016-08-04 | [32 empty] | AMNH
2016-08-05 | [32 empty] | AMNH
2016-08-06
2016-08-07

## Detailed Schedule
Month | Day | Time (EDT) | Cruise Event | Sentry Dive | Alvin Dive | Ship-Side | AT Transit | AT MBES_WCD | Telepresence Event | ISC 12h Watch | ISC Tasks | Notes
July | 28 | 4:00 | All leg 1 science party aboard Atlantis
4:30
5:00
5:30
|  | 6:00 | Atlantis Departs WHOI - Start Leg 1 |  |  |  | 13 h |  |  |  |  | 0600 is first tide window on 7/28. Final departure time TBD in consultation with Atlantis Master.
|  | 6:30 |  |  |  |  | 130 NM
|  | 7:00 | Atlantis Breakfast |  |  |  | 0600-1900
|  | 7:30 | Atlantis Breakfast
8:00
8:30
|  | 9:00 | ISC On-Line
9:30
|  | 10:00 | Training Session | [7 empty] | Training Session
|  | 10:30 | Training Session | [7 empty] | Training Session
11:00
|  | 11:30 | Atlantis Lunch
|  | 12:00 | Atlantis Lunch
12:30
|  | 13:00 | Alvin/Sentry Planning Meeting | [7 empty] | Alvin/Sentry Planning Meeting
|  | 13:30 | Alvin/Sentry Planning Meeting | [7 empty] | Alvin/Sentry Planning Meeting
14:00
14:30
15:00
15:30
16:00
16:30
17:00
|  | 17:30 | Atlantis Dinner
|  | 18:00 | Science Debrief | [7 empty] | Science Debrief
|  | 18:30 | Atlantis Arrives Veatch Canyon 2 / Science Debrief | [7 empty] | Science Debrief
19:00
19:30
|  | 20:00 | Deploy Sentry Veatch Canyon 2 / Reports | Mission 1 | [6 empty] | Reports
|  | 20:30 | Reports / ISC Off-Line | 10 h | [6 empty] | Reports
|  | 21:00 |  | 2000-0600
21:30
|  | 22:00 | Multicore / Gravity Core/CTD Collection |  |  | CTD + Coring | [5 empty] | Require Sentry team approval for over the side operations during deployment
|  | 22:30 |  |  |  | 6 h
23:00
23:30
| 29 | 0:00
0:30
1:00
1:30
2:00
2:30
3:00
3:30
4:00
4:30
5:00
|  | 5:30 | Recover Sentry Veatch Canyon 2
6:00
|  | 6:30 | Atlantis Transit to Engineering Dive Site |  |  |  | 1 h
|  | 7:00 | Atlantis Arrive Engineering Dive Site / Atlantis Breakfast |  |  |  | ? NM
|  | 7:30 | Atlantis Breakfast
|  | 8:00 | Launch Alvin Engineering Dive |  | ENG | [6 empty] | Dive Location TBD by Alvin Group. Assuming within 1 hour of Sentry dive location.
|  | 8:30 |  |  | 9 h
|  | 9:00 | ISC On-Line |  | 0800-1700 | [5 empty] | Process Sentry mission 1 data for use in planning Alvin dive on July 30
9:30
|  | 10:00 | Training Session | [7 empty] | Training Session
|  | 10:30 | Training Session | [7 empty] | Training Session
11:00
|  | 11:30 | Atlantis Lunch
|  | 12:00 | Atlantis Lunch
12:30
|  | 13:00 | Alvin/Sentry Planning Meeting | [7 empty] | Alvin/Sentry Planning Meeting
|  | 13:30 | Alvin/Sentry Planning Meeting | [7 empty] | Alvin/Sentry Planning Meeting
14:00
14:30
15:00
15:30
16:00
|  | 16:30 | Recover Alvin Engineering Dive
17:00
|  | 17:30 | Atlantis Dinner
|  | 18:00 | Atlantis Transit to New England Seep 2 / Science Debrief |  |  |  | 1 h |  |  |  | Science Debrief
|  | 18:30 | Atlantis Arrive New England Seep 2 / Science Debrief |  |  |  | ? NM |  |  |  | Science Debrief
19:00
|  | 19:30 | Deploy Sentry New England Seep 2 | Mission 2
|  | 20:00 | Reports | 9.5 h | [6 empty] | Reports
|  | 20:30 | Reports / ISC Off-Line | 1930-0500 | [6 empty] | Reports
21:00
|  | 21:30 | Multicore / Gravity Core/CTD Collection |  |  | CTD + Coring | [5 empty] | Require Sentry team approval for over the side operations during deployment
|  | 22:00 |  |  |  | 5.5 h
22:30
23:00
23:30
| 30 | 0:00
0:30
1:00
1:30
2:00
2:30
3:00
3:30
4:00
|  | 4:30 | Recover Sentry New England Seep 2
5:00
|  | 5:30 | Atlantis Transit to Veatch Canyon 2 |  |  |  | 2 h
|  | 6:00 |  |  |  |  | 18 NM
|  | 6:30 |  |  |  |  | 05:30 - 07:30
|  | 7:00 | Atlantis Arrive Veatch Canyon 2 / Atlantis Breakfast
|  | 7:30 | Atlantis Breakfast
|  | 8:00 | Launch Alvin Dive Veatch Canyon 2 |  | Dive 1
|  | 8:30 |  |  | 9 h
|  | 9:00 | ISC On-Line |  | 0800-1700 | [5 empty] | Process Sentry mission 2 data for use in planning Alvin dive on July 31
9:30
|  | 10:00 | Training Session | [7 empty] | Training Session
|  | 10:30 | Training Session | [7 empty] | Training Session
11:00
|  | 11:30 | Atlantis Lunch
|  | 12:00 | Atlantis Lunch
12:30
|  | 13:00 | Alvin/Sentry Planning Meeting | [7 empty] | Alvin/Sentry Planning Meeting
|  | 13:30 | Alvin/Sentry Planning Meeting | [7 empty] | Alvin/Sentry Planning Meeting
14:00
14:30
15:00
15:30
16:00
|  | 16:30 | Recover Alvin Dive Veatch Canyon 2
17:00
|  | 17:30 | Atlantis Dinner
|  | 18:00 | Atlantis Transit to Veatch Canyon 1 / Science Debrief |  |  |  | <0.25 h |  |  |  | Science Debrief
|  | 18:30 | Atlantis Arrive Veatch Canyon 1/ Science Debrief |  |  |  | 0.5 NM |  |  |  | Science Debrief
19:00
|  | 19:30 | Deploy Sentry Veatch Canyon 1 | Mission 3
|  | 20:00 | Reports | 9.5 h | [6 empty] | Reports
|  | 20:30 | Reports / ISC Off-Line | 1930-0500 | [6 empty] | Reports
21:00
|  | 21:30 | Multicore / Gravity Core/CTD Collection |  |  | CTD + Coring | [5 empty] | Require Sentry team approval for over the side operations during deployment
|  | 22:00 |  |  |  | 5.5 h
22:30
23:00
23:30
| 31 | 0:00
0:30
1:00
1:30
2:00
2:30
3:00
3:30
4:00
|  | 4:30 | Recover Sentry Veatch Canyon 1
5:00
|  | 5:30 | Atlantis Transit to New England Seep 2 |  |  |  | 2 h
|  | 6:00 |  |  |  |  | 17 NM
|  | 6:30 |  |  |  |  | 05:30 - 07:30
|  | 7:00 | Atlantis Arrive New England Seep 2 / Atlantis Breakfast
|  | 7:30 | Atlantis Breakfast
|  | 8:00 | Launch Alvin Dive New England Seep 2 |  | Dive 2
|  | 8:30 |  |  | 9 h
|  | 9:00 | ISC On-Line |  | 0800-1700 | [5 empty] | Process Sentry mission 3 data for use in planning Alvin dive on Aug 6
9:30
|  | 10:00 | Training Session | [7 empty] | Training Session
|  | 10:30 | Training Session | [7 empty] | Training Session
11:00
|  | 11:30 | Atlantis Lunch
|  | 12:00 | Atlantis Lunch
12:30
|  | 13:00 | Alvin/Sentry Planning Meeting | [7 empty] | Alvin/Sentry Planning Meeting
|  | 13:30 | Alvin/Sentry Planning Meeting | [7 empty] | Alvin/Sentry Planning Meeting
14:00
14:30
15:00
15:30
|  | 16:00 | [8 empty] | AMNH Show Rehersal
|  | 16:30 | Recover Alvin Dive New England Seep 2 | [7 empty] | AMNH Show Rehersal
17:00
|  | 17:30 | Atlantis Dinner
|  | 18:00 | Atlantis Transit to New England Seep 3 / Science Debrief |  |  |  | 0.5 h |  |  |  | Science Debrief
|  | 18:30 | Atlantis Arrive New England Seep 3 / Science Debrief |  |  |  | 3 NM |  |  |  | Science Debrief
19:00
|  | 19:30 | Deploy Sentry New England Seep 3 | Mission 4
|  | 20:00 | Reports | 10.5 h | [6 empty] | Reports
|  | 20:30 | Reports / ISC Off-Line | 1930-0600 | [6 empty] | Reports
21:00
|  | 21:30 | Multicore / Gravity Core/CTD Collection |  |  | CTD + Coring | [5 empty] | Require Sentry team approval for over the side operations during deployment
|  | 22:00 |  |  |  | 6.5 h
22:30
23:00
23:30
August | 1 | 0:00
0:30
1:00
1:30
2:00
2:30
3:00
3:30
4:00
4:30
5:00
|  | 5:30 | Recover Sentry New England Seep 3
6:00
|  | 6:30 | Atlantis Transit to Shallop Canyon West |  |  |  | 1 h
|  | 7:00 | Atlantis Arrive Shallop Canyon West / Atlantis Breakfast |  |  |  | 9 NM
|  | 7:30 | Atlantis Breakfast
|  | 8:00 | Launch Alvin Dive Shallop Canyon West |  | Dive 3 | [6 empty] | Bounce Dive. Depth = 373.5 m
|  | 8:30 |  |  | 3.5 h
|  | 9:00 | ISC On-Line |  | 0800-1130 | [5 empty] | Process Sentry mission 4 data for use in planning Alvin dive on Aug 5
9:30
|  | 10:00 | Training Session | [7 empty] | Training Session
|  | 10:30 | Training Session | [7 empty] | Training Session
|  | 11:00 | Recover Alvin Dive Shallop Canyon West
|  | 11:30 | Atlantis Lunch
|  | 12:00 | Atlantis Lunch
12:30
|  | 13:00 | [8 empty] | Alvin/Sentry Planning Meeting | Bounce Dive. Depth = 373.5 m
|  | 13:30 | Launch Alvin Dive Shallop Canyon West / Alvin/Sentry Planning Meeting |  | Dive 4 | [5 empty] | Alvin/Sentry Planning Meeting
|  | 14:00 | Alvin/Sentry Planning Meeting |  | 3.5 h
|  | 14:30 |  |  | 1330-1700
15:00
15:30
16:00
|  | 16:30 | Recover Alvin Dive Shallop Canyon West
17:00
|  | 17:30 | Atlantis Dinner
|  | 18:00 | Science Debrief |  |  | CTD + Coring |  |  |  |  | Science Debrief | Require Sentry team approval for over the side operations during deployment
|  | 18:30 | Science Debrief |  |  | 3 h |  |  |  |  | Science Debrief
19:00
19:30
|  | 20:00 | Reports | [7 empty] | Reports
|  | 20:30 | Reports / ISC Off-Line | [7 empty] | Reports
|  | 21:00 | Atlantis Transit to WHOI |  |  |  | 13.5 h
|  | 21:30 |  |  |  |  | 131 NM
|  | 22:00 |  |  |  |  | 2100-1030
22:30
23:00
23:30
| 2 | 0:00
0:30
1:00
1:30
2:00
2:30
3:00
3:30
4:00
4:30
5:00
5:30
6:00
6:30
|  | 7:00 | Cohort B Transit URI to WHOI | [7 empty] | Overland Transit
|  | 7:30 | Atlantis Breakfast | [7 empty] | Overland Transit
|  | 8:00 | Atlantis Breakfast | [7 empty] | Overland Transit
|  | 8:30 | [8 empty] | Overland Transit
|  | 9:00 | Cohort B Arrive WHOI | [7 empty] | Overland Transit
9:30
10:00
|  | 10:30 | Atlantis Arrive WHOI End Leg 1 | [8 empty] | 11:00 is tide window. Intend rapid personnel swap on same tide. ~1 hour.
|  | 11:00 | Science Party Transfer
|  | 11:30 | Atlantis Departs WHOI Start Leg 2 |  |  |  | 13.5 h
|  | 12:00 | Cohort A transit WHOI to URI |  |  |  | 131 NM |  |  |  | Overland Transit
|  | 12:30 |  |  |  |  | 1130-0100 |  |  |  | Overland Transit
|  | 13:00 | [8 empty] | Overland Transit
|  | 13:30 | [8 empty] | Overland Transit
|  | 14:00 | Cohort A arrive URI | [7 empty] | Overland Transit
14:30
15:00
15:30
|  | 16:00 | ISC On-Line
16:30
17:00
|  | 17:30 | Atlantis Dinner
|  | 18:00 | Science Debrief | [7 empty] | Science Debrief
|  | 18:30 | Science Debrief | [7 empty] | Science Debrief
19:00
19:30
|  | 20:00 | Reports | [7 empty] | Reports
|  | 20:30 | Reports / ISC Off-Line | [7 empty] | Reports
21:00
21:30
22:00
22:30
23:00
23:30
| 3 | 0:00
|  | 0:30 | Atlantis Arrive Shallop Canyon East
1:00
|  | 1:30 | Deploy Sentry Shallop Canyon East | Mission 5
|  | 2:00 |  | 5 h
|  | 2:30 |  | 0130-0630
|  | 3:00 |  |  |  | CTD + Coring | [5 empty] | Require Sentry team approval for over the side operations during deployment
|  | 3:30 | Multicore / Gravity Core/CTD Collection |  |  | 2 h
4:00
4:30
5:00
5:30
|  | 6:00 | Recover Sentry Shallop Canyon East
6:30
|  | 7:00 | Atlantis Transit to Hydrographer Coral 2 / Atlantis Breakfast |  |  |  | 0.5 h
|  | 7:30 | Atlantis Breakfast
|  | 8:00 | Launch Alvin Hydrographer Coral 2 |  | Dive 5
|  | 8:30 |  |  | 9 h
|  | 9:00 | ISC On-Line |  | 0800-1700 | [5 empty] | Process Sentry mission 5 data for use in planning Alvin dives on Aug 4
9:30
|  | 10:00 | Training Session | [7 empty] | Training Session
|  | 10:30 | Training Session | [7 empty] | Training Session
11:00
|  | 11:30 | Atlantis Lunch
|  | 12:00 | Atlantis Lunch
12:30
|  | 13:00 | Alvin/Sentry Planning Meeting | [7 empty] | Alvin/Sentry Planning Meeting
|  | 13:30 | Alvin/Sentry Planning Meeting | [7 empty] | Alvin/Sentry Planning Meeting
14:00
14:30
15:00
15:30
|  | 16:00 | [8 empty] | AMNH Show
|  | 16:30 | Recover Alvin Dive Hydrographer Coral 2 | [7 empty] | AMNH Show
17:00
|  | 17:30 | Atlantis Dinner
|  | 18:00 | Atlantis Transit to Shallop Canyon West/ Science Debrief |  |  |  | 1 h |  |  |  | Science Debrief
|  | 18:30 | Atlantis Arrive Shallop Canyon West / Science Debrief |  |  |  | 8 NM |  |  |  | Science Debrief
19:00
|  | 19:30 | Deploy Sentry Shallop Canyon West | Mission 6
|  | 20:00 | Reports | 11 h | [6 empty] | Reports
|  | 20:30 | Reports / ISC Off-Line | 1930-0630 | [6 empty] | Reports
21:00
|  | 21:30 | Multicore / Gravity Core/CTD Collection |  |  | CTD + Coring | [5 empty] | Require Sentry team approval for over the side operations during deployment
|  | 22:00 |  |  |  | 6.5 h
22:30
23:00
23:30
| 4 | 0:00
0:30
1:00
1:30
2:00
2:30
3:00
3:30
4:00
4:30
5:00
5:30
|  | 6:00 | Recover Sentry Shallop Canyon West
6:30
|  | 7:00 | Atlantis Transit to Shallop Canyon East / Atlantis Breakfast |  |  |  | 1 h
|  | 7:30 | Atlantis Breakfast
|  | 8:00 | Launch Alvin Dive Shallop Canyon East |  | Dive 6 | [6 empty] | Bounce Dive. Depth = 299.5 m
|  | 8:30 |  |  | 4 h
|  | 9:00 | ISC On-Line |  | 0800-1200
9:30
|  | 10:00 | Training Session | [7 empty] | Training Session
|  | 10:30 | Training Session | [7 empty] | Training Session
|  | 11:00 | Recover Alvin Dive Shallop Canyon East
|  | 11:30 | Atlantis Lunch
|  | 12:00 | Atlantis Lunch
12:30
|  | 13:00 | [8 empty] | Alvin/Sentry Planning Meeting | Bounce Dive. Depth = 299.5 m
|  | 13:30 | Launch Alvin Dive Shallop Canyon East / Alvin/Sentry Planning Meeting |  | Dive 7 | [5 empty] | Alvin/Sentry Planning Meeting
|  | 14:00 | Alvin/Sentry Planning Meeting |  | 4 h
|  | 14:30 |  |  | 1300-1700
15:00
15:30
|  | 16:00 | [8 empty] | AMNH Show
|  | 16:30 | Recover Alvin Dive Shallop Canyon East | [7 empty] | AMNH Show
17:00
|  | 17:30 | Atlantis Dinner
|  | 18:00 | Atlantis Transit to New England Seep 2/ Science Debrief |  |  |  | 1 h |  |  |  | Science Debrief
|  | 18:30 | Atlantis Arrive New England Seep 2/ Science Debrief |  |  |  | 8 NM |  |  |  | Science Debrief
19:00
|  | 19:30 | Deploy Sentry New England Seep 2 | Mission 7
|  | 20:00 | Reports | 11 h | [6 empty] | Reports
|  | 20:30 | Reports / ISC Off-Line | 1930-0630 | [6 empty] | Reports
21:00
|  | 21:30 | Multicore / Gravity Core/CTD Collection |  |  | CTD + Coring | [5 empty] | Require Sentry team approval for over the side operations during deployment
|  | 22:00 |  |  |  | 6.5 h
22:30
23:00
23:30
| 5 | 0:00
0:30
1:00
1:30
2:00
2:30
3:00
3:30
4:00
4:30
5:00
5:30
|  | 6:00 | Recover Sentry New England Seep 2
6:30
|  | 7:00 | Atlantis Transit to New England Seep 3/ Atlantis Breakfast |  |  |  | 0.5 h
|  | 7:30 | Atlantis Breakfast
|  | 8:00 | Launch Alvin Dive New England Seep 3 |  | Dive 8
|  | 8:30 |  |  | 9 h
|  | 9:00 | ISC On-Line |  | 0800-1700
9:30
|  | 10:00 | Training Session | [7 empty] | Training Session
|  | 10:30 | Training Session | [7 empty] | Training Session
11:00
|  | 11:30 | Atlantis Lunch
|  | 12:00 | Atlantis Lunch
12:30
|  | 13:00 | Alvin/Sentry Planning Meeting | [7 empty] | Alvin/Sentry Planning Meeting
|  | 13:30 | Alvin/Sentry Planning Meeting | [7 empty] | Alvin/Sentry Planning Meeting
14:00
14:30
15:00
15:30
|  | 16:00 | [8 empty] | AMNH Show
|  | 16:30 | Recover Alvin Dive New England Seep 3 | [7 empty] | AMNH Show
17:00
|  | 17:30 | Atlantis Dinner
|  | 18:00 | Atlantis Transit to Veatch Canyon 2/ Science Debrief |  |  |  | 2 h |  |  |  | Science Debrief
|  | 18:30 | Science Debrief |  |  |  | 17 NM |  |  |  | Science Debrief
|  | 19:00 |  |  |  |  | 1800-2000
|  | 19:30 | Atlantis Arrive New England Seep 2
|  | 20:00 | Reports | [7 empty] | Reports
|  | 20:30 | Deploy Sentry Veatch Canyon 2 / Reports / ISC Off-Line | Mission 8 | [6 empty] | Reports
|  | 21:00 |  | 10 h
|  | 21:30 |  | 2030-0630
22:00
|  | 22:30 | Multicore / Gravity Core/CTD Collection |  |  | CTD + Coring | [5 empty] | Require Sentry team approval for over the side operations during deployment
|  | 23:00 |  |  |  | 5.5 h
23:30
| 6 | 0:00
0:30
1:00
1:30
2:00
2:30
3:00
3:30
4:00
4:30
5:00
5:30
|  | 6:00 | Recover Sentry New England Seep 2
6:30
|  | 7:00 | Atlantis Transit to Veatch Canyon 1/ Atlantis Breakfast |  |  |  | 0.5 h
|  | 7:30 | Atlantis Breakfast
|  | 8:00 | Launch Alvin Dive Veatch Canyon 1 |  | Dive 9
|  | 8:30 |  |  | 9 h
|  | 9:00 | ISC On-Line |  | 0800-1700
9:30
|  | 10:00 | Training Session | [7 empty] | Training Session
|  | 10:30 | Training Session | [7 empty] | Training Session
11:00
|  | 11:30 | Atlantis Lunch
|  | 12:00 | Atlantis Lunch
12:30
|  | 13:00 | Alvin/Sentry Planning Meeting | [7 empty] | Alvin/Sentry Planning Meeting
|  | 13:30 | Alvin/Sentry Planning Meeting | [7 empty] | Alvin/Sentry Planning Meeting
14:00
14:30
15:00
15:30
16:00
|  | 16:30 | Recover Alvin Veatch Canyon 1
17:00
|  | 17:30 | Atlantis Dinner
|  | 18:00 | Science Debrief |  |  |  | 13 h |  |  |  | Science Debrief
|  | 18:30 | Science Debrief |  |  |  | 130 NM |  |  |  | Science Debrief
|  | 19:00 |  |  |  |  | 1800-0700
19:30
|  | 20:00 | Reports | [7 empty] | Reports
|  | 20:30 | Reports / ISC Off-Line | [7 empty] | Reports
21:00
21:30
22:00
22:30
23:00
23:30
| 7 | 0:00
0:30
1:00
1:30
2:00
2:30
3:00
3:30
4:00
4:30
5:00
5:30
6:00
6:30
|  | 7:00 | Atlantis Arrive WHOI End Leg 2 | [8 empty] | 7:30 is the tide window