## Shipping Logistics
NAAMES CRUISE SHIPPING AND LOGISTICS
Cruise Number: AT38
Mob days: Aug 26, 27, 28, 29 (Sat,Sun,M,T)
Dep: 30 Aug 2017 Woods Hole |  |  | NOTE: Van #5 Aresol SIO has requested to be loaded on may want a specific
Arr: 24 Sept 2017 Woods Hole |  |  | time to power off before loading and power on and interent when loaded to minimize time between calibration
DeMob Sept 25, 26 (M,T) |  |  | See link for pallet info | https://docs.google.com/spreadsheets/d/1RWoDkaQK2_-eEzqbzOjQxDL8zLNRpNl67RGLYmV1ivY/edit#gid=1169756740
Van Loading: Aug 26th, 110T Baxter crane booked |  |  | See link for gas cylinder info | https://docs.google.com/spreadsheets/d/1RWoDkaQK2_-eEzqbzOjQxDL8zLNRpNl67RGLYmV1ivY/edit#gid=1169756740
|  |  | See link for Chem info | https://docs.google.com/spreadsheets/d/1aK2tdQNhQS2ZE5RJzRCCL2zmYbpMuEbcsKXtKIObgs8/edit#gid=379758133
CONTAINERS
# | Container | Provied By | POC/Science | Location On Ship | Notes | Est Weight Lbs | Weight of van with equipment before loading onto ship or estimate of weight of equipment to be loaded into the van Lbs | Power/Other | Date Shipped from origin | Date of Arrival at WHOI | Storage Location at WHOI | Date needed on dock | Date load onto vessel *Baxter 110T crane has been booked
1 | Isotope Van | WHOI | WHOI David Fisichella/Chris Griner Rad Authorization submitted | 02 Deck, Port side- outside | *science party has requested a multi vial scintillation counter also swipe of van before use | 11000 | 8,000 plus LSC and gear? | Standard Power for WHOI Isotope Van Also need regular water hook up to the sink (Fresh Water) | at WHOI Shipping & Receiving ? | at WHOI Shipping & Receiving ? | Shipping & Receiving | 25-Aug? | 2017-08-26
2 | Lab Van w/Hood | UNOLS (arriving from UK to WHOI) | Peter Gaube <pgaube@apl.washington.edu> Kristina.Mojica@oregonstate.edu | Main Deck Port Side | UNOLS supplied van, power requirements are 25 amps "clean" power and 14.1 amps dirty power at 110 VAC | 11000 | 8,000lbs plus gear? | From UNOLS van pool website: 60 Hz electrical system. capable of operation from 208, 240 or 460 (440 to 480) V single-phase systems CHRIS HAS REMOVED BENCHES AND EYE WASH 7/24 | Safely Office parking lot | Safely Office parking lot | Safely Office parking lot | 24-Aug/early as possible on 25-Aug, sci party arrives early on 25th (EC) | 2017-08-26
3 | Aerosol - AreoChem | NOAA | Derek Coffman/aerosol measurements | 02 Deck Forward (Port side-outside) | Needs clean seawater to bow for this van. Have confirmed there is a connection there for this. We plan on setting up exactly as we have the past 2 cruises. We have a splitter box that we plug both vans (AeroChem and AeroPhys) into. We also plug the blower for the seasweep into this splitter box. We then plug this splitter box into the provided outlet on the ship. We need at least 60A of 440V, 3phase power for all. | 14500 | 14500 | 440V see notes DO NOT NEED POWER ON THE DOCK Just van access to offlaod gear | 2017-08-11 | 2017-08-18 | Shipping & Receiving ? | On dock by end of day on 24th so can unload equipment on the 25th | 2017-08-26
4 | Aerosol - Areo Phys | NOAA | Derek Coffman/aerosol measurements | 02 Deck Forward (Port side - inside) | We plan on setting up exactly as we have the past 2 cruises. We have a splitter box that we plug both vans (AeroChem and AeroPhys) into. We also plug the blower for the seasweep into this splitter box. We then plug this splitter box into the provided outlet on the ship. We need at least 60A of 440V, 3phase power for all. | 16300 | 16300 | 440V see notes DO NOT NEED POWER ON THE DOCK Just van access to offlaod gear | 2017-08-11 | 2017-08-18 | Shipping & Receiving | On dock by end of day on 24th so can unload equipment on the 25th | 2017-08-26
5 | Aerosol -SIO | Scripps Lynn Russell/TAMU Sarah Brooks | Lynn Russell Raghu Betha <rbetha@ucsd.edu> | 02 Deck Forward (Starboard side -inside) |  | 13000 | 13000 | 120 amps “clean” continuous power at 110 VAC. Lynn Russel will provide a 408 transformer. |  | Aug 15 by 3pm, been told to send to Shipping and Receiving Mae S Chu <mae@globallogisticsshipping.com> Robbie is point of contact | Shipping & Receiving | 8/21 need van at dock; 8/22 at 8am need power to van, 10am need small crane to lift inlet. | 2017-08-26
6 | Aerosol UNOLS Lab | UNOLS (using clean Isotope from Del) | Tom Bell tbe@pml.ac.uk UNOLS van/Fisichella or Griner | 3 Deck Forward (Starboard side -outside) | Preferred mounting is on feet or rails 2’ above deck. ~22 pallets arrive during the week of the 14th-20th August. This needs to be kept under cover please need this gear on dock on/before Aug 24 | 8000 | 13,000 lbs total (8,000van and 5,000 gear) | From UNOLS van pool website: 60 Hz electrical system. capable of operation from 208, 240 or 460 (440 to 480) V single-phase systems Input power to the shore side connector is 120/240/ 60 amp. Shipped from UNOLS van pool on 21st, arrive on 22nd | Ship from UNOLS Del on Aug 21 | Arrive Aug 22 | Bring directly to the WHOI DOCK? | 8/22 need power to van, science will set up on 8/23 (EC) ~22 pallets arrive during the week of the 14th-20th August. | 2017-08-26
7 | NOAA Storage Van | NOAA Bates | Derek Coffman/aerosol measurements | 02 Deck Port Side (inside) | We need at least 60A of 440V, 3phase power for all. We actually need 2 connections for the storage van. The one you mention is for our air compressor and it is a 3-phase 208 (240)V motor that draws 13-14A. This is the same as on the last NAAMES cruise. We also need to plug into a 110V outlet for lights, etc in the storage van. This is also as we have done in the past. " | 11000 | 2016 Deck plan has 17,500lb for this. | 3-phase 208 (or 240) V plug in ROV hanger | 2017-08-11 | 2017-08-18 | Shipping & Receiving | On dock by end of day on 24th so can unload equipment on the 25th | 2017-08-26
NA | 10' NOAA Storage Van | NOAA - At WHOI | Derek Coffman/Storage van not going to sea | Lifted onto ship on 26th, unload contents then offloaded back onto dock and left at WHOI during cruise | Lifted onto ship on 26th, unload contents then offloaded back onto dock and left at WHOI during cruise |  | ? |  | At WHOI ESL building | At WHOI ESL building | At WHOI ESL building | On dock by end of day on 24th so can unload equipment on the 25th | 26 Aug loaded on deck, unload contents and offloaded on dock
Other Deliveries | Susanne Menden-Duer from URI will be dropping of tanks at WHOI on Aug 9th | Susanne Menden-Deuer <smenden@uri.edu>
Tom Bell shipping 22 + pallets week of Aug 14