## CALIBRATION
EM122 Patch Test Settings |  |  | 2019 PLANNING
Vessel: |  |  | ATLANTIS
Area: |  |  | San Francisco, CA
Line Acquistion Information
Test | Pre-test settings | Transit to Cal | Pitch Pass 1 | Turn | Pitch Pass 2 | Transit A to C | XBT | Roll Pass 1 | Turn D to D | Roll Pass 2 | Transit C to H | XBT | Yaw Pass 1 | Transit G to F | Yaw Pass 1 | Transit G to A | Est. Transit to Cal Hours | Est. Cal. Hrs
XBT Prior to Line |  |  | Yes |  | No |  |  | No |  | No |  |  | No |  | No
EM122 SIS Line Number
Start Point (see figure) |  |  | A |  | B |  |  | C |  | D |  |  | H |  | F
End Point (see figure) |  |  | B |  | A |  |  | D |  | C |  |  | G |  | E
Speed (kts) |  | 10 | 8 | 8 | 8 | 10 |  | 8 | 8 | 8 | 10 |  | 8 | 10 | 8 | 10
Distance (nm) |  |  | 9.9892 |  | 9.9892 | 6.4795 |  | 8.0994 |  | 8.0994 | 11.3391 |  | 9.9892 | 10 | 9.9892 | 8.2
Course Over Ground |  |  | 135 |  | 315 |  |  | 45 |  | 225 |  |  | 135 |  | 135
Time (est. minutes) |  | 0 | 74.919 | 15 | 74.919 | 38.8769 | 15 | 60.7451 | 15 | 60.7451 | 68.0346 | 15 | 74.919 | 60 | 74.919 | 49.2 | 0 | 11.6213
EM122 MRU Angle (SIS, START)
EM122 Initial Calibration Adjustment
EM122 Verification Adjustment
EM122 MRU Angle (SIS, FINAL)
Notes
Environment & General Information
Test | Pre-test |  | Pitch Pass 1 | Turn | Pitch Pass 2 | Transit |  | Roll Pass 1 | Turn | Roll Pass 1 | Transit |  | Heading Line 1 | Transit | Heading Line 2 | Transit
Winds (kts)
Seas (m)
Start Time (GMT)
End Time (GMT)
Sonar Runtime Parameters
Sector Coverage | Pre-test |  | Pitch Pass 1 | Turn | Pitch Pass 2 | Transit |  | Roll Pass 1 | Turn | Roll Pass 1 | Transit |  | Heading Line 1 | Transit | Heading Line 2 | Transit
Max angle (port) |  |  | 30 |  | 30 |  |  | 70 |  | 70 |  |  | 60 |  | 10
Max angle (sbtd) |  |  | 30 |  | 30 |  |  | 70 |  | 70 |  |  | 10 |  | 60
Max Coverage (port) |  |  | 5000 |  | 5000 |  |  | 5000 |  | 5000 |  |  | 5000 |  | 5000
Max Coverage (stbd) |  |  | 5000 |  | 5000 |  |  | 5000 |  | 5000 |  |  | 5000 |  | 5000
Angular Coverage Mode |  |  | AUTO |  | AUTO |  |  | AUTO |  | AUTO |  |  | AUTO |  | AUTO
Beam Spacing |  |  | HD EQDST |  | HD EQDST |  |  | HD EQDST |  | HD EQDST |  |  | HD EQDST |  | HD EQDST
Depth Settings | Pre-test |  | Pitch Pass 1 | Turn | Pitch Pass 2 | Transit |  | Roll Pass 1 | Turn | Roll Pass 1 | Transit |  | Heading Line 1 | Transit | Heading Line 2 | Transit
Force Depth |  |  | n/a |  | n/a |  |  | n/a |  | n/a |  |  | n/a |  | n/a
Min depth (m)
Max depth (m)
Dual swath mode |  |  | DYNAMIC |  | DYNAMIC |  |  | DYNAMIC |  | DYNAMIC |  |  | DYNAMIC |  | DYNAMIC
Ping mode |  |  | AUTO |  | AUTO |  |  | AUTO |  | AUTO |  |  | AUTO |  | AUTO
FM disable |  |  | Unchecked |  | Unchecked |  |  | Unchecked |  | Unchecked |  |  | Unchecked |  | Unchecked
Transmit Control | Pre-test |  | Pitch Pass 1 | Turn | Pitch Pass 2 | Transit |  | Roll Pass 1 | Turn | Roll Pass 1 | Transit |  | Heading Line 1 | Transit | Heading Line 2 | Transit
Pitch stabilization |  |  | ENABLED |  | ENABLED |  |  | ENABLED |  | ENABLED |  |  | ENABLED |  | ENABLED
Along direction |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0
Auto Tilt |  |  | OFF |  | OFF |  |  | OFF |  | OFF |  |  | OFF |  | OFF
Yaw stab. Mode |  |  | REL. MEAN HDG*** |  | REL. MEAN HDG*** |  |  | REL. MEAN HDG*** |  | REL. MEAN HDG*** |  |  | REL. MEAN HDG*** |  | REL. MEAN HDG***
***NOTE: TURN OFF YAW STABILIZATION DURING TURNS, THEN TURN BACK ON TO REL. MEAN HDG. AFTER THE SHIP IS LINED UP FOR EACH SURVEY PASS.
heading |  |  | n/a |  | n/a |  |  | n/a |  | n/a |  |  | n/a |  | n/a
heading filter |  |  | MEDIUM |  | MEDIUM |  |  | MEDIUM |  | MEDIUM |  |  | MEDIUM |  | MEDIUM
Min Swath Dist |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0
Enable Scanning |  |  | Off |  | Off |  |  | Off |  | Off |  |  | Off |  | Off
Sound Speed | Pre-test |  | Pitch Pass 1 | Turn | Pitch Pass 2 | Transit |  | Roll Pass 1 | Turn | Roll Pass 1 | Transit |  | Yaw Line 1 | Transit | Yaw Line 2 | Transit
Source |  |  | SENSOR |  | SENSOR |  |  | SENSOR |  | SENSOR |  |  | SENSOR |  | SENSOR
Filters and Gains | Pre-test |  | Pitch Pass 1 | Turn | Pitch Pass 2 | Transit |  | Roll Pass 1 | Turn | Roll Pass 1 | Transit |  | Heading Line 1 | Transit | Heading Line 2 | Transit
Spike Filter Strength |  |  | MEDIUM |  | MEDIUM |  |  | MEDIUM |  | MEDIUM |  |  | MEDIUM |  | MEDIUM
Range Gate |  |  | NORMAL |  | NORMAL |  |  | NORMAL |  | NORMAL |  |  | NORMAL |  | NORMAL
Phase Ramp |  |  | NORMAL |  | NORMAL |  |  | NORMAL |  | NORMAL |  |  | NORMAL |  | NORMAL
Penetration Filter Strength |  |  | WEAK |  | WEAK |  |  | WEAK |  | WEAK |  |  | WEAK |  | WEAK
Slope |  |  | Checked |  | Checked |  |  | Checked |  | Checked |  |  | Checked |  | Checked
Aeration |  |  | Unchecked |  | Unchecked |  |  | Unchecked |  | Unchecked |  |  | Unchecked |  | Unchecked
Sector Tracking |  |  | Unchecked |  | Unchecked |  |  | Unchecked |  | Unchecked |  |  | Unchecked |  | Unchecked
Intereference |  |  | Unchecked |  | Unchecked |  |  | Unchecked |  | Unchecked |  |  | Unchecked |  | Unchecked
Normal incidence corr. (deg) |  |  | 6 |  | 6 |  |  | 6 |  | 6 |  |  | 6 |  | 6
Use Lambert's Law |  |  | Unchecked |  | Unchecked |  |  | Unchecked |  | Unchecked |  |  | Unchecked |  | Unchecked
Absorption Coefficent Source |  |  | CTD Profile |  | CTD Profile |  |  | CTD Profile |  | CTD Profile |  |  | CTD Profile |  | CTD Profile
Salinty (parts per thousand) |  |  | 35 |  | 35 |  |  | 35 |  | 35 |  |  | 35 |  | 35
TX power level (dB) |  |  | Max |  | Max |  |  | Max |  | Max |  |  | Max |  | Max
Soft startup ramp time |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0
Water Column log R |  |  | 30 |  | 30 |  |  | 30 |  | 30 |  |  | 30 |  | 30
dB Offset
Special Mode Sonar |  |  | Unchecked |  | Unchecked |  |  | Unchecked |  | Unchecked |  |  | Unchecked |  | Unchecked

## WAYPOINTS
| Waypoint | Decimal Degrees |  | Degrees Decimal Minutes
|  | Lat. | Lon. | Lat. Deg. | Lat. Min. | Lon. Deg. | Lon. Min.
Pitch | A | 35.7861 | -122.7992 | 35 | 47.1669 | -122 | 47.9505
| B | 35.6678 | -122.6549 | 35 | 40.0705 | -122 | 39.2959
Roll | C | 35.8472 | -122.9138 | 35 | 50.8345 | -122 | 54.829
| D | 35.9427 | -122.7961 | 35 | 56.5638 | -122 | 47.7668
Heading 1 | E | 35.7778 | -122.8094 | 35 | 46.6706 | -122 | 48.562
| F | 35.6596 | -122.6651 | 35 | 39.5749 | -122 | 39.9074
Heading 2 | G | 35.7944 | -122.789 | 35 | 47.6632 | -122 | 47.3389
| H | 35.6761 | -122.6447 | 35 | 40.566 | -122 | 38.6843

## LINE PLAN IMAGE
NOTE: ORDER OF WAYPOINTS MAY CHANGE DEPENDING ON SEA STATE, OTHER TESTING, TRANSIT CONSTRAINTS, ETC.
G A E
H B F
C
D
EM122
calibration area
San Francisco
Tentative Alvin operations area at 34.5 N, 123.0 W from email on 5 Dec 2018