## Atlantis_2019
Cruise Plan for CCE1, CCE2, CORC3 & Del Mar cruise 2019
R/V Atlantis
AT42-10: Ohman "CCE-LTER3"
Paul Chua
Scripps Institution of Oceanography
sunrise 06:04, sunset 19:28
From | To |  | nautical twilight: 05:07 & 20:25
2019-04-27 08:00 | 2019-05-03 16:30 | [5 empty] | Actual 11 knots
Time start | Time end | hours (hh:mm) | Activity | Starting point | End Point | Distance in nautical miles | transit (hrs) @10 knots
2019-04-27 08:00 | 2019-04-27 08:00 |  | Depart Marfac, San Diego
2019-04-27 08:00 | 2019-04-27 09:00 | 0.041667 | Harbor transit
2019-04-27 09:00 | 2019-04-27 12:00 | 0.125 | Transit to Del Mar Buoy |  | 32° 55.810'N, 117° 19.030'W | 30 | 3
2019-04-27 12:00 | 2019-04-27 12:00 | 0 | Arrive Del Mar Buoy
2019-04-27 12:00 | 2019-04-27 13:00 | 0.041667 | CTD Cast 1 pre-recovery calibration casts to 90m for instrument calibration near Del Mar Surface Mooring
2019-04-27 13:00 | 2019-04-27 16:00 | 0.125 | Recover Del Mar Buoy
2019-04-27 16:00 | 2019-04-27 17:00 | 0.041667 | WBAT Acoustic Coms
2019-04-27 17:00 | 2019-04-27 18:00 | 0.041667 | Transit to CCE2 site via CTD calibration site |  | 33° 1.379'N, 117° 28.991'W | 10 | 1
2019-04-27 18:00 | 2019-04-27 20:00 | 0.083333 | CTD Cast 2 pre-deployment calibration cast to 300m for instrument calibration; water samples (S, O); attach 2 Microcats ODO, 3 Seacats w/ FLNTUS & 1 acoustic release to CTD rosette.
2019-04-27 20:00 | 2019-04-27 22:00 | 0.083333 | Transit to CCE2 site via CTD calibration site |  | 33° 12.715'N, 117° 48.337'W | 20 | 2
2019-04-27 22:00 | 2019-04-28 | 0.083333 | CTD Cast 3 pre-deployment calibration cast to 50m for instrument calibration; water samples (O, S, chl, nuts, C); attach Biopackage Cage, 1 Seacat w/ FLNTUS, & 1 Seaphox to CTD rosette.
2019-04-28 | 2019-04-28 09:00 | 0.375 | Transit to CCE2 site via deep CTD calibration site |  | 33° 45.813'N, 119° 29.433'W | 90 | 9
2019-04-28 09:00 | 2019-04-28 11:00 | 0.083333 | CTD Cast 4 pre-deployment calibration casts to 1800m for instrument calibration; water samples (S, O?); attach microcats to CTD Rosette & 2 Acoustic Release
2019-04-28 11:00 | 2019-04-28 18:30 | 0.3125 | Continue transit to CCE2 site |  |  | 75 | 7.5
2019-04-28 18:30 | 2019-04-28 18:30 | 0 | Arrive CCE2
2019-04-28 18:30 | 2019-04-29 02:30 | 0.33333 | Deploy CCE2-11 |  | 34° 18.12'N, 120° 48.84'W
2019-04-29 02:30 | 2019-04-29 12:30 | 0.41667 | Transit to CCE1 site |  |  | 100 | 10
2019-04-29 12:30 | 2019-04-29 12:30 | 0 | Arrive at CCE1 site
2019-04-29 12:30 | 2019-04-29 13:30 | 0.041667 | CTD Cast 5 calibration cast to 1000m near CCE1 buoy; water samples (O, S, chl, nuts, C);attach 1000m microcats to CTD Rosette
2019-04-29 13:30 | 2019-04-29 20:30 | 0.29167 | CCE1-12 Recovery |  | 33° 28.57'N, 119° 31.61'W
2019-04-29 20:30 | 2019-04-29 22:30 | 0.083333 | CTD Cast 6 pre-deployment calibration cast to 50m for instrument calibration between two CCE2 buoys; water samples (O, S, chl, nuts, C); attach Biopackage Cage to CTD rosette.
2019-04-29 22:30 | 2019-04-30 06:30 | 0.33333 | Downtime
2019-04-30 06:30 | 2019-04-30 08:30 | 0.083333 | Setup for CCE1-13
2019-04-30 08:30 | 2019-04-30 10:30 | 0.083333 | CCE1 Drift Test
2019-04-30 10:30 | 2019-04-30 20:30 | 0.41667 | Deployment of CCE1-13 |  | 33° 28.57'N, 119° 31.61'W
2019-04-30 20:30 | 2019-04-30 22:30 | 0.083333 | CTD Cast 7 post-deployment calibration cast to 50m for instrument calibration; water samples (O, S, chl, nuts, C); attach CCE1 Biopackage Cage to CTD rosette.
2019-04-30 22:30 | 2019-04-30 23:30 | 0.041667 | water sampling
2019-04-30 23:30 | 2019-05-01 00:30 | 0.041667 | CTD Cast 8 calibration cast to 1000m near CCE1 buoy; water samples (O, S)
2019-05-01 00:30 | 2019-05-01 02:30 | 0.083333 | Mooring Verificaiton
2019-05-01 02:30 | 2019-05-01 12:30 | 0.41667 | Transit to CCE2 site |  |  | 100 | 10
2019-05-01 12:30 | 2019-05-01 12:30 | 0 | Arrive at CCE2 site
2019-05-01 12:30 | 2019-05-01 17:30 | 0.20833 | CCE2-10 Recovery |  | 34° 18.59'N, 120° 48.83'W
2019-05-01 17:30 | 2019-05-01 19:30 | 0.083333 | CTD Cast 9 post-deployment calibration casts to 600m for instrument calibration between CCE Buoys; water samples (O, S, chl, nuts, C); attach Seacat w/o FLNTUS to CTD rosette
2019-05-01 19:30 | 2019-05-01 20:30 | 0.041667 | Mooring Verificaiton
2019-05-01 20:30 | 2019-05-01 22:30 | 0.083333 | CTD Cast 10 post-deployment calibration cast to 50m for instrument calibration near CCE2 buoy; water samples (O, S, chl, nuts, C); attach CCE1 Biopackage Cage to CTD rosette.
2019-05-01 22:30 | 2019-05-02 13:30 | 0.625 | Transit to CORC3 |  |  | 150 | 15
2019-05-02 13:30 | 2019-05-02 13:30 | 0 | Arrive CORC3 site
2019-05-02 13:30 | 2019-05-02 16:30 | 0.125 | Recover PIES |  | 33° 18.30'N, 119° 2.04'W
2019-05-02 16:30 | 2019-05-02 19:30 | 0.125 | Deploy PIES
2019-05-02 19:30 | 2019-05-02 20:30 | 0.041667 | Triangulate PIES
2019-05-02 20:30 | 2019-05-02 22:30 | 0.083333 | CTD Cast 11 post-deployment calibration cast to 800m near CORC3-3 PIES for instrument calibration; water samples (S)
2019-05-02 22:30 | 2019-05-03 00:30 | 0.083333 | Acoustic data communication to download data from CORC3-03 mooring |  | 33° 18.02'N, 119° 1.77'W
2019-05-03 00:30 | 2019-05-03 05:30 | 0.20833 | Transit to deep CTD11 site |  | 32° 33.876'N, 118° 6.129'W | 50 | 5
2019-05-03 05:30 | 2019-05-03 07:30 | 0.083333 | CTD Cast 12 post-deployment calibration cast to 1800m for instrument calibration; water samples (S); attach Microcats to CTD rosette.
2019-05-03 07:30 | 2019-05-03 10:30 | 0.125 | Weather Reserve
2019-05-03 10:30 | 2019-05-03 15:30 | 0.20833 | Transit to San Diego |  |  | 50 | 5
2019-05-03 15:30 | 2019-05-03 16:30 | 0.041667 | Harbor transit
2019-05-03 16:30 | 2019-05-03 16:30 | 0 | Arrive Marfac, San Diego
|  | 1900-01-05 08:30 |  |  |  | 675 | 67.5 | <- 10 knots
[7 empty] | 61.3636 | <- 11 knots | 6.1364
[7 empty] | 56.25 | <- 12 knots | 11.25
Formulas:
To = [From]+SUM(C12:C58)
To = [To, row above]+[hours (hh:mm)]
From = [To, row above]
hours (hh:mm) = SUM(C11:[hours (hh:mm), row above])

## Waypoints
Cruise Plan for CCE1, CCE2, CORC3 & Del Mar cruise 2019
R/V Atlantis
AT42-10: Ohman "CCE-LTER3"
Paul Chua
Scripps Institution of Oceanography
Site | Position
Del Mar Buoy | 32° 55.810'N, 117° 19.030'W
CORC3-03 | 33° 18.02'N, 119° 1.77'W
CORC3 PIES | 33° 18.30'N, 119° 2.04'W
CCE2-10 | 34° 18.12'N, 120° 48.84'W
CCE2-11 | 34° 18.59'N, 120° 48.83'W
CCE1-12 & CCE1-13 | 33° 28.57'N, 119° 31.61'W
CTD site 1 | at Del Mar Buoy
CTD site 2 | 33° 1.379'N, 117° 28.991'W
CTD site 3 | 33° 12.715'N, 117° 48.337'W
CTD site 4 | 33° 45.813'N, 119° 29.433'W
CTD site 5 | at CCE1 buoy
CTD site 6 | at CCE1 buoy
CTD site 7 | at CCE1 buoy
CTD site 8 | at CCE1 buoy
CTD site 9 | at CCE2 buoy
CTD site 10 | at CCE2 buoy
CTD site 11 | At CORC3 PIES
CTD site 12 | 32° 33.876'N, 118° 6.129'W

## Task Description
Cruise Plan for CCE1, CCE2, CORC3 & Del Mar cruise 2019
R/V Atlantis
AT42-10: Ohman "CCE-LTER3"
Paul Chua
Scripps Institution of Oceanography
Operation Name | Task | Overboard Equipment Depth (m) | Est. Operations Area (nm)
CTD Cast #1 | CTD Cast 1 pre-recovery calibration casts to 90m for instrument calibration near Del Mar Surface Mooring | 90 | 0.5
Recover Del Mar Buoy | Recovery of Del Mar Surface Buoy | 100 (full) | 1
CTD Cast #2 | CTD Cast 2 pre-deployment calibration cast to 300m for instrument calibration; water samples (S, O); attach 2 Microcats ODO, 3 Seacats w/ FLNTUS & 1 acoustic release to CTD rosette. | 300 | 0.5
CTD Cast #3 | CTD Cast 3 pre-deployment calibration cast to 50m for instrument calibration; water samples (O, S, chl, nuts, C); attach Biopackage Cage, 1 Seacat w/ FLNTUS, & 1 Seaphox to CTD rosette. | 50 | 0.5
CTD Cast #4 | CTD Cast 4 pre-deployment calibration casts to 1800m for instrument calibration; water samples (S, O?); attach microcats to CTD Rosette & 2 Acoustic Release | 1800 | 2
Deployment of CCE2-11 | Deployment of CCE2-11 surface mooring | 800 (full) | 10
CTD Cast #5 | CTD Cast 5 calibration cast to 1000m near CCE1 buoy; water samples (O, S, chl, nuts, C);attach 1000m microcats to CTD Rosette | 1000 | 1
CCE1-12 Recovery | Recovery of CCE1-12 surface mooring. | 4000 (full) | 10
CTD Cast #6 | CTD Cast 6 pre-deployment calibration cast to 50m for instrument calibration between two CCE2 buoys; water samples (O, S, chl, nuts, C); attach Biopackage Cage to CTD rosette. | 50 | 0.5
Deployment of CCE1-13 | Deployment of CCE1-13 surface mooring | 4000 (full) | 10
CTD Cast #7 | CTD Cast 7 post-deployment calibration cast to 50m for instrument calibration; water samples (O, S, chl, nuts, C); attach CCE1 Biopackage Cage to CTD rosette. | 50 | 0.5
CTD Cast #8 | CTD Cast 8 calibration cast to 1000m near CCE1 buoy; water samples (O, S) | 1000 | 1
CCE2-10 Recovery | Recovery of CCE2-10 surface mooring. | 800 (full) | 10
CTD Cast #9 | CTD Cast 9 post-deployment calibration casts to 600m for instrument calibration between CCE Buoys; water samples (O, S, chl, nuts, C); attach Seacat w/o FLNTUS to CTD rosette | 600 | 1
CTD Cast #10 | CTD Cast 10 post-deployment calibration cast to 50m for instrument calibration near CCE2 buoy; water samples (O, S, chl, nuts, C); attach CCE1 Biopackage Cage to CTD rosette. | 50 | 0.5
CORC3 PIES Recovery | Recovery of CORC3 PIES Bottom Lander | 800 (full) | 1
CORC3 PIES Deployment | Deployment of CORC3 PIES Bottom Lander | 800 (full) | 1
CTD Cast #11 | CTD Cast 11 post-deployment calibration cast to 750m near CORC3-3 PIES for instrument calibration; water samples (S) | 750 | 1
CORC3-03 Mooring Communication | Acoustic data communication to download data from CORC3-03 mooring | 15 | 0.5
CTD Cast #12 | CTD Cast 12 post-deployment calibration cast to 1800m for instrument calibration; water samples (S); attach Microcats to CTD rosette. | 1800 | 2

## Navy
Cruise Plan for CCE1, CCE2, CORC3 & Del Mar cruise 2019
R/V Atlantis
AT42-10: Ohman "CCE-LTER3"
Paul Chua
Scripps Institution of Oceanography
Station | Task | Waypoint | Start (local) | Finish (local) | SR Area | Overboard Equip. Depth (m) | Est. Operations Area (nm) | Operation Name
1 | CTD, overboard operations | 32° 55.810'N, 117° 19.030'W | 271200APR19 | 271300APR19 | ? | 90 | 0.5 | CTD Cast #1
2 | Recovery of surface Mooring | 32° 55.810'N, 117° 19.030'W | 271300APR19 | 271600APR19 | ? | 100 (full) | 1 | Recover Del Mar Buoy
3 | CTD, overboard operations | 33° 1.379'N, 117° 28.991'W | 271800APR19 | 272000APR19 | ? | 300 | 0.5 | CTD Cast #2
4 | CTD, overboard operations | 33° 12.715'N, 117° 48.337'W | 272200APR19 | 280000APR19 | ? | 50 | 0.5 | CTD Cast #3
5 | CTD, overboard operations | 33° 45.813'N, 119° 29.433'W | 280900APR19 | 281100APR19 | W289S 3B | 1800 | 2 | CTD Cast #4
6 | Deployment surface mooring | 34° 18.59'N, 120° 48.83'W | 281830APR19 | 290230APR19 | W537 | 800 (full) | 10 | Deployment of CCE2-11
7 | CTD, overboard operations | 33° 28.57'N, 119° 31.61'W | 291230APR19 | 291330APR19 | W537 | 1000 | 1 | CTD Cast #5
8 | Recovery of surface mooring | 33° 28.57'N, 119° 31.61'W | 291330APR19 | 292030APR19 | W537 | 4000 (full) | 10 | Recovery of CCE1-12
9 | CTD, overboard operations | 33° 28.57'N, 119° 31.61'W | 292030APR19 | 292230APR19 | W537 | 50 | 0.5 | CTD Cast #6
10 | Deployment of surface mooring | 33° 28.57'N, 119° 31.61'W | 301030APR19 | 302030APR19 | W537 | 4000 (full) | 10 | Deployment of CCE1-13
11 | CTD, overboard operations | 33° 28.57'N, 119° 31.61'W | 302030APR19 | 302230APR19 | W537 | 50 | 0.5 | CTD Cast #7
12 | CTD, overboard operations | 33° 28.57'N, 119° 31.61'W | 302330APR19 | 010030MAY19 | W537 | 1000 | 1 | CTD Cast #8
13 | Recovery of surface mooring | 34° 18.12'N, 120° 48.84'W | 011230MAY19 | 011730MAY19 | W537 | 800 (full) | 10 | Recovery of CCE2-10
14 | CTD, overboard operations | 34° 18.12'N, 120° 48.84'W | 011730MAY19 | 011930MAY19 | W537 | 600 | 1 | CTD Cast #9
15 | CTD, overboard operations | 34° 18.12'N, 120° 48.84'W | 012030MAY19 | 012230MAY19 | W537 | 50 | 0.5 | CTD Cast #10
16 | Recovery & redeployment bottom lander | 33° 18.30'N, 119° 2.04'W | 021330MAY19 | 021930MAY19 | W291 | 800 (full) | 1 | CORC PIES
17 | CTD, overboard operations | 33° 18.30'N, 119° 2.04'W | 022030MAY19 | 022230MAY19 |  | 750 | 1 | CTD Cast #11
18 | Acoustic communications | 33° 18.02'N, 119° 1.77'W | 022230MAY19 | 030030MAY19 | W291 | 15 | 0.5 | CORC3-Mooring ACOMS
19 | CTD, overboard operations | 32° 33.876'N, 118° 6.129'W | 030530MAY19 | 030730MAY19 | W291 | 1800 | 2 | CTD Cast #12