## Sheet1
WHOI ship time
Timeline: 5.5 science days, ~2 days transit, 1 day multibeam cals, 3 additional hours EcoCTD, 4 hours deploy/recovery X-Spar, remainder transits and CTDs
Rough time estimates | Station Number | Station Name | Latitude (deg/min N) | Longitude (deg/min W) | CTD max Depth (m) | Notes
Depart: 17-Nov-2019 09:00:00
Transit: Woods Hole to EM710 site = 10 hrs
Begin: 17-Nov-2019 09:00:00
Finish: 17-Nov-2019 19:00:00
| 1 | T1 | 41 29.4383 | 70 39.165
| 2 | T2 | 41 22.5517 | 70 52.2283
| 3 | T3 | 41 14.515 | 70 51.4383
Multibeam: EM710 patch test (5 hrs) + EcoCTD extra time (1.5 hrs) = total 6.5 hrs
Begin: 17-Nov-2019 19:00:00
Finish: 18-Nov-2019 01:30:00
| 1 | EM710A | 39 58.6541 | 70 15.4440 |  | run A to B, then B to A @ 8kts
| 2 | EM710B | 39 56.3929 | 70 12.4233
| 3 | EM710C | 39 59.4583 | 70 16.5640 |  | run C to D, then D to C @ 8kts
| 4 | EM710D | 40 2.1262 | 70 16.0031
| 5 | EM710E | 39 58.4992 | 70 15.6401 |  | run E to F @ 8kts
| 6 | EM710F | 39 56.2379 | 70 12.6192
| 7 | EM710G | 39 58.8092 | 70 15.2483 |  | run G to H @ 8kts
| 8 | EM710H | 39 56.5478 | 70 12.2274
Transit: EM710 to EM122 = 15 hrs
Begin: 18-Nov-2019 01:30:00
Finish: 18-Nov-2019 16:30:00
CTD sampling mode part 1: 3 CTDs for salinometer test and ARGO cals = 6 hrs
Begin: 18-Nov-2019 16:30:00
Finish: 18-Nov-2019 22:30:00
| 1 | SS1 | 39 44 | 67 00 | 2000
| 2 | SS1 | 39 44 | 67 00 | 2000
| 3 | SS1 | 39 44 | 67 00 | 2000
Multibeam: EM122 patch test (12 hrs) + EcoCTD extra time (1.5 hr) = toal 13.5 hrs
Begin: 18-Nov-2019 22:30:00
Finish: 19-Nov-2019 12:00:00
| 1 | EM122A | 39 53.7404 | 66 55.9889
| 2 | EM122B | 39 47.2996 | 66 55.0118
| 3 | EM122C | 39 44.0056 | 66 51.9301
| 4 | EM122D | 39 37.5943 | 66 50.6708
| 5 | EM122E | 39 53.6178 | 66 57.3477
| 6 | EM122F | 39 47.1771 | 66 56.3684
| 7 | EM122G | 39 53.8627 | 66 54.6301
| 8 | EM122H | 39 47.4218 | 66 53.6550
Deploy X-Spar: (can move earlier if needed) = 2 hrs | [5 empty] | *a few miles down wind of SS1 site, Working assumption of 0.03-0.12 knots drift for buoy
Begin: 19-Nov-2019 12:00:00
Finish: 19-Nov-2019 14:00:00
CTD sampling mode part 2: CTDs for fit test (2.5 hrs for full-depth CTD, 0.5 hrs for sampling and setup) = total 24 hrs
Begin: 19-Nov-2019 14:00:00
Finish: 20-Nov-2019 14:00:00
| 1 | SS1 | 39 44 | 67 00 | bottom
| 2 | SS1 | 39 44 | 67 00 | bottom
| 3 | SS1 | 39 44 | 67 00 | bottom
| 4 | SS1 | 39 44 | 67 00 | bottom
| 5 | SS1 | 39 44 | 67 00 | bottom
| 6 | SS1 | 39 44 | 67 00 | bottom
| 7 | SS1 | 39 44 | 67 00 | bottom
| 8 | SS1 | 39 44 | 67 00 | bottom
CTD sampling mode part 3: CTDs for salinometer test and ARGO cals = 12 hrs
Begin: 20-Nov-2019 14:00:00
Finish: 21-Nov-2019 02:00:00
| 1 | SS1 | 39 44 | 67 00 | 2000
| 2 | SS1 | 39 44 | 67 00 | 2000
| 3 | SS1 | 39 44 | 67 00 | 2000
| 4 | SS1 | 39 44 | 67 00 | 2000
| 5 | SS1 | 39 44 | 67 00 | 2000
| 6 | SS1 | 39 44 | 67 00 | 2000
Transit to X-Spar: (drift over 51 hours @0.03 knots = 1.53 nm, @0.12 = 6.12 nm) estimate = 0.5 hrs
Begin: 21-Nov-2019 02:00:00
Finish: 21-Nov-2019 02:30:00
| 1 | X-SPAR drift | 39 54 | 67 10
Recovery X-Spar: (do CTDs or EcoCTD testing before if needed) = 2 hrs
Begin: 21-Nov-2019 02:30:00
Finish: 21-Nov-2019 04:30:00
Transit: Back to WH = 22 hrs
Begin: 21-Nov-2019 04:30:00
Finish: 22-Nov-2019 02:30:00
| 1 | T6 | 41 14.515 | 70 51.4383
| 2 | T7 | 41 22.5517 | 70 52.2283
| 3 | T8 | 41 29.4383 | 70 39.165
Arrive WH: 22-Nov-2019 02:30:00